## Sheet1
CR # | Change Description | Requester | Date Raised | Decision | Comment
1 | Church info not easy to find. Make more prominent | Marje Caie | 2016-04-16 | Approved | Church info added to landing page. All info a facsimile of www.burtonwilts.org.uk
2 | Revise top level menu - slim down and iron out wrinkles. | Chris Bennett | 2021-10-26 | Approved | Encourage contributors to use Categories and to add a featured image
3 | Enlarge heading 'Burton in Wiltshire' on landing page. | Chris Bennett | 2021-10-26 | Approved | removed the Buttons section to make way for large title. As a result, the Church info is less prominent (see CR1)
4 | Sidebars to be relevant to post category. | Chris Bennett | 2021-10-26 | Approved | Reduced variety of sidebars
5 | About Burton webpage – revise text. | Amanda Read | 2021-10-26 | Approved | Reduced to basic history of Burton, pending further posts on the topic.
6 | Improve SEO | Amanda Read | 2021-10-26 | Approved | Ongoing
7 | Community Question Board. Options: (i) a community forum; (ii) a static ‘Mine of Information' page with villagers self-nominating for specific areas of expertise. | Bugle Feedback | 2021-10-26 | Pending | Option (i) will require moderators. A standalone forum has been set up, but further discussion required before it is published.
8 | Add Privacy and cookie policy | Amanda Read | 2021-10-26 | Approved | Cookie policy banner added to website.
9 | Delete Editor accounts for those who have left the village | Amanda Read | 2021-10-26 | Approved
10 | GDPR – Action on CWB to check BCA form covers website | Amanda Read | 2021-10-26 | Approved | CWB confirmed BCA form includes GDPR cover for the website.
11 | Twitter and Instagram feed - AJR | Chris Bennett | 2021-10-26 | Approved | Social media sharing buttons appear at foot of posts.
12 | Set of Icons – BCA, Book Club, The Bugle, 100 Club | Amanda Read | 2021-10-26 | Approved | CWB sent AJR the 100 Club logo.
13 | Subscribe button - make more prominent | Amanda Read | 2021-11-01 | Approved
14 | Subscribe button - resolve WP issue | Lee Jane Hawkes | 2021-11-01 | Approved
15 | Add an Editor account for NHW coordinator | Amanda Read | 2021-11-02 | Pending | AJR awaiting details from NHW coordinator
16 | Add transparent (ie black on transparent background) BCA logo to landing page | Amanda Read | 2021-11-02 | Approved